## Summary
Self-Learning Audit Report — 2026-04-03
Metric | Value | Status | Notes
Total Tasks (all-time) | 786 | OK
All-time Success Rate | 31% | WARN | Dominated by early failures (tasks 1-600)
Recent-50 Success Rate | 98% | OK | Dramatic improvement since task ~600
Recent-20 Success Rate | 95% | OK | Consistent high performance
First-Pass Success Rate | 57% | WARN | Room for improvement; retries compensate
Timeout Rate | 27% | BAD | 212 timeouts; 90% are zero-step (planner budget)
Zero-Step Timeout Rate | 90% | BAD | Planner consumes entire budget before step 1
Improvement Velocity | +10.4 pp/100 tasks | OK | Steady upward trajectory
Learning Rules | 20/20 | OK | At cap; dedup working
Zombie Tasks | 20 (166 wasted slots) | WARN | Archived, guard in place
Registry Size | 91 KB (11 tasks) | OK | Well under 512KB threshold
Pipeline State | IDLE | OK | 0 running, 0 queued, 0 approved
Retry Classification | 100% | OK | All 146 retries classified
External Signals | Stale (9 days) | WARN | Last signal 2026-03-25

## Learning Trend
Success Rate by Task Window
Window | Success Rate | Timeouts | Phase
1-50 | 34% | 19 | Early exploration
51-100 | 4% | 5 | Learning dip
101-150 | 6% | 33 | Timeout crisis
151-200 | 4% | 38 | Timeout crisis peak
201-250 | 16% | 34 | Partial recovery
251-300 | 10% | 23 | Stabilizing
301-350 | 14% | 5 | Timeout fix applied
351-400 | 12% | 12 | Plateau
401-450 | 22% | 29 | Regression
451-500 | 26% | 20 | Gradual improvement
501-550 | 10% | 23 | Regression
551-600 | 14% | 8 | Pre-breakthrough
601-650 | 58% | 1 | BREAKTHROUGH
651-700 | 86% | 1 | Rapid improvement
701-750 | 96% | 0 | Near-perfect
751-786 | 97% | 1 | Sustained excellence

## Findings & Fixes
Problems Found and Actions Taken
# | Problem | Severity | Root Cause | Action Taken | Status
1 | Repetitive task loop: 4 tasks ran 95x with no new value | HIGH | Weakness detector re-detects resolved milestones after 2h cooldown expires | Archived 100 entries to context-archive.md. GLOBAL_FAMILY_SUCCESS_CAP=8 already guards against future repeats. | FIXED
2 | Stale alerts: retry_churn + loop_effort active while pipeline is IDLE | MEDIUM | Alert clear logic requires manual trigger; background sync re-asserts stale flags from metrics | Cleared alerts.json. Note: background sync may re-assert from stale metrics.json; metrics need simultaneous update. | FIXED (recurring)
3 | Metrics drift: task_registry_total=15 (actual=11), learning_rules=31 (actual=20) | MEDIUM | Metrics not recomputed from registry after compaction; cross-project registry adds phantom counts | Updated metrics.json with correct values. Background sync reverts; long-term fix needs validate-metrics.sh integration. | PARTIALLY FIXED
4 | context.md bloated to 400 lines / 18K tokens | MEDIUM | No pruning triggered when task entries exceed threshold; 100 entries for only 7 unique tasks | Compacted to ~30 lines with summary table. Full history archived to context-archive.md. | FIXED
5 | Self-improve stuck in cooldown_active | LOW | All task families either at success cap or in cooldown; no new weaknesses detected | This is correct behavior — pipeline is idle and healthy. Growth-mode rule exists but needs trigger. | BY DESIGN
6 | External signals stale (9 days) | LOW | Signal source (OpenAI Python releases) hasn't published new release since 2026-03-25 | No action needed — staleness reflects source, not system failure. | EXPECTED

## Repetition Analysis
Task Repetition Analysis (context.md)
Task Family | Total Runs | Successes | Failures | Wasted Runs (>1) | Assessment
Verify trigger-aware credential recovery routing | 29 | 29 | 0 | 28 | 28 runs wasted — task succeeds every time
Inventory decision path for dashboard incident id | 27 | 27 | 0 | 26 | 26 runs wasted — pure repetition
Verify dashboard incident id field in smoke flow | 23 | 22 | 1 | 21 | 21 runs wasted — 1 failure out of 23
Verify dashboard incident payload coverage | 16 | 14 | 2 | 13 | 13 runs wasted — detection keeps re-firing
Fix value measurement blindness | 3 | 3 | 0 | 2 | Borderline — 3 runs acceptable
Inventory for payload coverage | 1 | 1 | 0 | 0 | OK — single run
Inventory for trigger-aware routing | 1 | 1 | 0 | 0 | OK — single run
TOTAL | 100 | 97 | 3 | 90 | 90% of all runs were wasted repetitions